## Sheet1
Date | Owner | Component | Owner | Component | Owner | Component | Owner | Component
23/10/2013 | Adithya | Database Design | Vinay | Device and student authentication and acknowledgment mechanism | Pavan | Login Screen | Alok
24/10/2013 | Adthya | Database Design | Vinay | Student Dashboard Screen | Pavan | Faculty DashBoard - Displays Various Operations faculty can perform - Publish key answers, start a test., schedule a test, create a test, publish results, display results
25/10/2013 |  | Q and A View | Vinay | History Screen | Pavan | Schedule Test Screen - Contains information about created unscheduled test.
23/10/2013 |  | Device and student authentication and acknowledgment mechanism | Vinay
24/10/2013 |  | Student Dashboard Screen | Vinay
25/10/2013 |  | History Screen | Vinay

## Sheet3
Jyothy Institute of Technology Project Work Breakdown Structure
Project Title: Sensor Enable Robot For Personal Assistance Guide: Prithvi Kumar
PHASE1-Building Entry Exit Counter Circuit using Sensors and Relay
Date | Team Member 1-Rajatha | Team Member 2-Arjun | Team Member 3-Manohar | Team Member 4-Pragathi
2016-09-09 |  |  |  | Introduction to sensor
2016-09-12 | POP3 architecture
2016-09-15 | Automation |  |  | spech recognition
2016-10-09 | Arduino Uno architecture | Arduino Uno board architecture | Arduino Uno board architecture | Arduino Uno board architecture
2016-10-10 | Aayudha pooja | Aayudha pooja | Aayudha pooja | Aayudha pooja
2016-10-11 | Vijyadashmi | Vijyadashmi | Vijyadashmi | Vijyadashmi
2016-10-12 | Trip | Trip | Trip | Trip
2016-10-13 | Trip | Trip | Trip | Trip
2016-10-14 | Trip | Trip | Trip | Trip
2016-10-15 | Trip | Arduino Uno board Architecture | Transistor Working | relay working
2016-10-16 | prepation of wbs | learning color coding of resistor | lcd working | Function
2016-10-17 | Arduino Uno board Architecture | create github account | create github account | prepare project abstract
2016-10-18 | stand up meeting with team | stand up meeting with team | stand up meeting with team | stand up meeting with team
2016-10-19 | placement preparation | placement preperation | placement preperation | placement preperation
2016-10-20 | placement | placement | placement | placement
2016-10-21 | entry exit controller circuit | updating of srs to github account | Coding for the circuit | Coding for the circuit
2016-10-22 | Building entry exit counter circuit | Building circuit | Building circuit | circuit working
2016-10-23 | Review by Panel members | Review by Panel members | Review by Panel members | Review by Panel members
2016-10-24 | stand up meeting with project guide | stand up meeting with project guide | stand up meeting with project guide | stand up meeting with project guide
2016-10-25 | Placement preparation | Placement preparation | Placement preparation | Placement preparation
2016-10-26 | Placement | placement | Placement | Placement
2016-10-27 | designing test cases | desiging test cases | Violin concert | updating project diary
2016-10-28 | Running test cases | Running test cases | Running test cases | Running test cases
2016-10-29 | Feedback from guide | Feedback from Guide | Feedback from Guide | Feedback from Guide
2016-10-30 | diwali | diwali | diwali | diwali
2016-10-31 | break | break | break | break
PHASE 2-Automatic light on/off and temperature detection(Yet To Plan)
2016-11-01 | types of sensors | light sensors | temperature sensor | preparing use case diagram
2016-11-02 | preparing Sequence diagram | temperature sensor types | light sensor | type of sensors
2016-11-03 | CGI Placement drive | preparing DFD | learning coding for temperature sensor | CGI Placement drive
2016-11-04 | learning code for ldr | light sensor implementation | light sensor implementation | Trip
2016-11-05 | break | break | break | Trip
2016-11-06 | break | break | break | Trip
2016-11-07 | coding for ldr | light resistor-ldr | coding for lm35 | updating documentation
2016-11-08 | stand up meeting with team | stand up meeting with team | stand up meeting with team | stand up meeting with team
2016-11-09 | stand up meeting with guide | stand up meeting with guide | stand up meeting with guide | stand up meeting with guide
2016-11-10 | IBM placement drive | break | volin program | IBM placement drive
2016-11-11 | break | updating github | debugging errors in code of lm35 | updating project diary
2016-11-12 | Internals preparation | Internals preparation | Internals preparation | Internals preparation
2016-11-13 | Internals preparation | Internals preparation | Internals preparation | Internals preparation
2016-11-14 | internals | internals | Internals | internals
2016-11-15 | internals | internals | internals | internals
2016-11-16 | internals | internals | internals | internals
2016-11-17 | break | break | break | break
2016-11-18 | stand up meeting with team | stand up meeting with team | stand up meeting with team | stand up meeting with team
2016-11-19 | web lab internals | web lab internals | web lab internals | web lab internals
2016-11-20 | stand up meeting with project guide | stand up meeting with project guide | stand up meeting with project guide | stand up meeting with project guide
2016-11-21 | lab internals preparation | lab internals preparation | lab internals preparation | lab internals preparation
2016-11-22 | networks lab internal | networks lab internal | networks lab internal | networks lab internal
2016-11-30 | preparation for lab externals | preparation for lab externals | preparation for lab externals | preparation for lab externals
2016-12-06 | preparation for externals | preparation for externals | preparation for externals | preparation for externals
2017-01-09 | stand up meeting with project guide | stand up meeting with project guide | stand up meeting with project guide | stand up meeting with project guide
2017-01-22 | circuit building | circuit building | circuit building | circuit building
2017-01-23 | circuit building | circuit building | circuit building | circuit building
24/1/2017 | implementing ldr code | implementing lm35 code | implementing lm35 code | updating circuit in project diary
25/1/2017 | Peer junction interview | Peer junction interview | Peer junction interview | Peer junction interview
26/1/2017 | technical seminar work | debugging circuit | merging ldr and lm35 code | technical seminar work
27/1/2017 | Trigent Interview | Trigent Interview | Trigent Interview | Trigent Interview
2017-01-28 | stand up meeting with guide | stand up meeting with guide | stand up meeting with guide | stand up meeting with guide
2017-01-29 | design test cases | updating project diary | desing test cases | updating github
2017-01-30 | Running test cases | Running test cases | Running test cases | Running test cases
31/1/2017 | feedback from Guide | Feedback from Guide | review and feedback from Guide | review and feedback from guide
2017-02-01 | team outing | team outing | team outing | team outing
2/2/2017 | verification &validation from HOD | verification &validation from HOD | verification &validation from HOD | verification &validation from HOD
PHASE 3-Voice Recoginisation
2017-02-13 | Binary Titans interview | Binary Titans interview | Binary Titans interview | Binary Titans interview
2017-02-14 | meeting with guide wrt phase 3 | meeting with guide wrt phase 3 | meeting with guide wrt phase 3 | meeting with guide wrt phase 3
2017-02-15 | technical seminar work | introduction study on voice recognition | vilon program | introduction study on voice recognition
2017-02-16 | function | break | introduction to voice sensors | break
2017-02-17 | Function | technical seminar work | technical seminar work | technical seminar work
2017-02-18 | reassembling phase1 & phase2 ckt | reassembling phase1 & phase2 ckt | reassembling phase1 & phase2 ckt | reassembling phase1 & phase2 ckt
2017-02-19 | reassembling phase1 & phase2 ckt | reassembling phase1 & phase2 ckt | reassembling phase1 & phase2 ckt | reassembling phase1 & phase2 ckt
2017-02-20 | updating wbs | updating srs | updating srs | updating wbs
2017-02-21 | Magna infotech Interview | Magna infotech Interview | Magna infotech Interview | Magna infotech Interview
2017-02-22 | introduction to voice recognition | soldering fan | debugging errors in code of lm35 | hoilday
2017-02-23 | 2nd round interview magna infotech | meeting with guide wrt review | meeting with guide wrt review | updating diary
2017-02-24 | updating wbs | updating github | preparing ppt | holiday-emergency
2017-02-25 | 2phase review by pannel members | 2phase review by pannel members | 2phase review by pannel members | 2phase review by pannel members
2017-02-26 | holiday | holiday | holiday | holiday
2017-02-27 | wireless networks | wired network | wireless network | wired network
2017-02-28 | circuit diagram study | circuit diagram study | code study | code study
2017-03-01 | meeting with guide wrt phase 3 | meeting with guide wrt phase3 | meeting with guide wrt phase3 | meeting with guide wrt phase3
2017-03-02 | circuit building | circuit building | implementing code | implementing code
2017-03-03 | circuit building | circuit building | implementing code | implementing code
2017-03-04 | design test cases | updating github | design test cases | updating diary
2017-03-05 | Running test cases | running test cases | running test cases | running test cases
2017-03-06 | feedback from Guide | feedback from Guide | feedback from Guide | feedback from Guide
PHASE 4-User Interface For Visual Feedback (Yet to plan)
2017-03-13 | types of user interface | how to build UI | study on UI | what is visual feedback
2017-03-14 | how to add buttons | how to add images | how to display output | what are the alternative ways to UI
2017-03-15 | stand up meeting with team | stand up meeting with team | stand up meeting with team | stand up meeting with team
2017-03-16 | accept visual feedback from user | building interactive buttons | accept visual feedback from user | building interactive buttons
2017-03-17 | design test cases | update git hub | design test cases | update project diary
2017-03-18 | stand up meeting with guide | stand up meeting with guide | stand up meeting with guide | stand up meeting with guide
2017-03-19 | runnig test cases | Running test cases | Running test cases | Running test cases
2017-03-20 | review and feedback from guide | review and feedback from guide | review and feedback from guide | review and feedback from guide
2017-03-31 | integrate all phases | integrate all phases | integrate all phases | integrate all phases
2017-04-01 | verification and validation | verification and validation | verification and validation | verification and validation
2017-04-02 | report making | report making | report making | report making